### Review of the Game Logic Planning Document (KILO)

#### 1. Timing Issues & Unrealistic Deadlines

- Connect Four

  - GUI implementation starts too soon after logic completion (March 14-16).

  - No buffer period for debugging before GUI testing.

  - Final debugging scheduled too late (April 4), leaving no room for major fixes asTesting & Refinement of GUI → 16th MARCH 2025(what to do between 16 to 4)

  - Suggestion: Add 3-4 extra days for debugging before GUI integration.

- Checkers

  - No explicit milestone for testing the CLI version before GUI integration.

  - GUI integration (Week 5) has no buffer for logic changes from Week 3.

  - Suggestion: Add a dedicated debugging phase before GUI integration.

- Tic-Tac-Toe

  - Final debugging starts too close to submission (April 4).

  - GUI development (March 18-22) lacks buffer time for bug fixes.

  - Suggestion: Start GUI testing earlier (March 20-21) and allow debugging time before final submission.

#### 2. Risks That Could Impact Completion

- Dependencies Between Tasks

  - Game logic must be fully functional before GUI development, but no buffer is allocated for potential issues or bugs .

  - JavaFX integration is a risk if the team is unfamiliar with it.

  - Solution: Include a dedicated debugging phase before GUI work to make ure game logic is working properly.

- Resource Allocation Issues

  - No clear mention of task distribution among team members.

  - If one person handles too much (e.g., logic and GUI), delays may occur.

  - Solution: Assign clear roles and define contingency plans for missed deadlines.

#### 3. Suggestions for Timeline & Task Order

- Move unit tests for board logic earlier (March 10-12).

- Add debugging time before GUI development (March 15-17).

- Start GUI testing earlier (March 20-22).

- Allocate time for final testing before April 4.

- Use April 5-9 for documentation and packaging instead of bug fixes.

#### Final Verdict

What Works Well

- Structured approach: CLI before GUI.

- Well-defined phases and deadlines.

- Unit testing is included.

What Needs Improvement

- Add buffer time for debugging and testing.

- Account for dependencies between logic and GUI.

- Clearly define team responsibilities to prevent workload imbalances.

Final Recommendations

- Adjust task dependencies and debugging schedule.

- Plan for JavaFX integration challenges early.